ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Purpose of the Contract	2

2.2.	Results to be achieved by the Contractor	2

3.	ASSUMPTIONS & RISKS	2

3.1.	Assumptions underlying the project	2

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.1.1.	Project description	3

4.1.2.	Geographical area to be covered	3

4.1.3.	Target groups	3

4.2.	Specific work	3

4.3.	Project management	4

4.3.1.	Responsible person	4

4.3.2.	Facilities to be provided by the Contracting Authority and/or other parties	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & period of implementation	4

6.	REQUIREMENTS	4

6.1.	Staff	4

6.1.1.	Key experts	4

6.1.2.	Non-key experts	6

6.1.3.	Support staff & backstopping	6

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission & approval of reports	7

8.	MONITORING AND EVALUATION	7

8.1.	Special requirements	7

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting Authority

Health Center “Dr. Đorđe Lazić” Sombor, Mirna 3, 25000 Sombor, Republic of Serbia

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

The overall objective of the project is to harmonize and improve emergency medical assistance in the cross-border area with the aim of achieving greater efficiency and professionalism in preserving human lives, as well as providing a joint response in the event of major, mass disasters in the program area.

## Purpose of the Contract

The purposes of this contract are as follows:

(Activity 1) To translate the promotion materials, publications Croatian- Serbian – Hungarian languages (it depends on it is originally on which language).

(Activity 2) To implement digital marketing on public stationary display in City of Sombor in 1 location for 6 months minimal with video representations of providing first aid in case of sudden cardiac arrest.

(Activity 3) To creating promotional materials 200 pcs each( bags, t-shirts, pens, mugs), 1 roll-up, 1 plakate, 4000 leflets .

(Activity 4) Based on the professional publication on heart attack prevention, promotion of healthy lifestyles, first aid procedures with the alphabet of emergency aid the contractor needs tosecure the following services:  proofreading, graphic design, digital processing of 4000 publications, trilingual.

## Results to be achieved by the Contractor

- Translated promotion materials and publications.

- Successful digital marketing on public stationary display in City of Sombor on 1 location for 6 minimum months

- Created promotional materials 200 pcs each( bags, t-shirts, pens, mugs), 1 roll-up, 1 plakate, 4000 leaflets .

- Proofreaded, graphic designed, digital processed and printed 4000 copies altogether on 3 languages of the professional publication.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

Not applicable,

.

## Risks

Not applicable,

# SCOPE OF THE WORK

## General

### Project description

Project S.O.O.S. - Sombor Osijek Emergency Response Partnership represents an innovative cross-border initiative aimed at improving emergency medical assistance in the area of ​​Osijek-Baranja County (Croatia) and Western Balkan District (Serbia). The goal is to ensure timely, standardized and uniform emergency medical care for the local rural population, tourists and visitors, thereby directly contributing to increased survival in cases of sudden cardiac arrest and other emergencies. Cross-border cooperation in the exchange of knowledge, development of protocols and simulations of mass accidents was particularly emphasized, which will strengthen the capacities of the emergency aid system on both sides of the border. The project includes a wide range of activities from education, training, promotion and simulations to the establishment of the Teaching Center in Sombor, with the aim of strengthening capacity, reducing differences in the quality of services and increasing the safety of the population. Through the cooperation of Croatian and Serbian institutions, and the application of European standards and environmental norms, the project contributes to sustainable development, improving health infrastructure and promoting healthy lifestyles, thereby laying the foundations for a permanent and widely applicable improved emergency medical service in the border area.

### Geographical area to be covered

Sombor - West Bačka District /Autonomous Province of Vojvodina / Serbia

### Target groups

The target group of the project are :

- Rural population of the cross-border area

- Touristsand visitours of the region

- Medical and emergency personnel

- Local authorities and health institutions

- Non governmental and professional organisations

## Specific work

A.   To translate the promotion materials, publications Croatian- Serbian – Hungarian languages (it depends on it is originally on which language).

The consultant needs to secure translation service, of promotional materials and publications from Croatian to Serbian and Hungarian and from Serbian to Croatian and Hungarian. The translation should be accurate, clearly and accessible conveyed, and adapted to the target audience in the area of ​​cross-border cooperation. It includes the translation of brochures, leaflets, presentations, reports and other promotional content, while ensuring consistency and appropriate terminology in all languages. The service also includes the review and proofreading of translated materials to ensure quality and professional appearance. The goal is to enable efficient communication and promotion of the project in all relevant languages, ensuring that messages are understandable and accessible to all target groups in the region.

The number of pages/ documents that needs to be translated is from 30 to a maximum of 50 pages on 3 languages.

It should be made no later than 1 month from the signing of the contract

- To implement digital marketing on public stationary display in City of Sombor in 1 location for 6 months minimal with video representations of providing first aid in case of sudden cardiac arrest.

For the project the consultant needs to implement a digital marketing solution on a public stationary display in the City of Sombor, at one selected location, is required. The service includes the installation and maintenance of the digital display for at least 6 months, with regular showing of educational video content on first aid in case of sudden cardiac arrest. The goal is to increase awareness of the importance of modern response and training in first aid, in order to ensure a visually attractive and informative promotion. It includes the creation, adaptation and management of video content, as well as technical support and monitoring of the display throughout the campaign.

The stationary display needs to be minimum wide 1,5 m, Hight 2 m and it needs to be located near the town center of Sombor.

The displayed material needs to be in color HD resolution.

It should be made no later than 6 months from the signing of the contract

- To creating promotional materials (bags, t-shirts, pens, mugs), 1 roll-up, 1 billboard, 4000 leaflets.

The consultant needs to secure the following services:

To design and produce the promotional materials in a total volume of:

200 pieces of T-shirts various sizes

200 pieces of bags with the minimum size (wide20 cm, high 30 cm)

200 pieces of pens

200 pieces of mugs

1 roll-up

1 billboard

4000 leaflets with informative content, double-sided, colored, in 2 languages, on paper with 4 rages

All items need to be in accordance with the rules and visual identity of the program, and needs to contain the logo of the program and if it is possible the logo and/or the name of the project. The service includes the design, production, printing and delivery of all the aforementioned promotional materials.

It should be made no later than 2 months from the signing of the contract

- Based on the professional publication on heart attack prevention, promotion of healthy lifestyles, first aid procedures with the alphabet of emergency aid the contractor needs to secure the following services:  proofreading, graphic design, digital processing of 4000 publications, trilingual.

The contractor needs to secure the following services: printing of 4000 publications

The services include the following stages and details:

Proofreading and proofreading:

- Precise proofreading of all texts to ensure accuracy, clarity and coherence of the content.

- Correction of spelling, grammar and style errors, while respecting the professional and expert tone of the publication.

- Checking compliance with medical terms and standards.

Graphic design:

- Creation of an attractive and functional design adapted to target groups, with a clear visual identity that reflects the topics of prevention and emergency care.

- Design of the cover page, interior pages, titles, illustrations and infographics that facilitate understanding of the content.

- Creation of a design for a trilingual edition, while ensuring consistency and ease of reading in all languages.

Digital processing and prepress:

- Digital processing and formatting of the publication in accordance with the technical specifications of the printing house, including optimization of resolution, color and format.

- Quality control of digital files, including test printing if necessary.

Trilingual edition:

- Translation and adaptation of content into two additional languages, ensuring accuracy and clarity of the translation, as well as compliance with the original text. The translation needs to be on Serbian, Hungarian, English .

- Coordination of translation and graphic design for the trilingual edition, with the possibility of consulting with medical terminology experts.

Printing and delivery:

- Packing and delivery of final, prepared publications in agreed quantities and formats (4000 pieces)

- Printed in colure.

- Dimensions of the professional publication/book A4 (21 x 29.7 cm)

It should be made no later than 2 months from the signing of the contract

## Project management

### Responsible person

The responsible person for the overall implementation of the tasks related to this contract and for the coordination of specific activities and implementation of professional details, in the Contracting Authority is the legal representative of the organization Emeše Uri.

### Facilities to be provided by the Contracting Authority and/or other parties

No facilities will be provided.

# LOGISTICS AND TIMING

## Location

For the service: implement digital marketing on public stationary display

Place of performance: Sombor

For all other activities the location of service is not important.

## Start date & period of implementation

The intended start date is <date> and the period of implementation of the contract will be <number> months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

### Key experts

N/A

### Non-key experts

CVs for non-key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles.

The Contractor must select and hire other experts as required according to the profiles identified in the Organisation & Methodology and/or these Terms of Reference. All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Support staff & backstopping

The Contractor will provide support facilities to their team of experts (back-stopping) during the implementation of the contract.

Backstopping and support staff costs must be included in the fee rates.

## Office accommodation

Office accommodation is to be provided by the Contractor and costs are included in the contract value.

## Facilities to be provided by the Contractor

The Contractor must ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract that is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

Please see Article 26 of the General Conditions. There must be a final report accompanied by a final invoice at the end of the period of implementation of the tasks.

The Contractor will submit the following reports in English language in one original and one copy:

| Name of report | Content | Time of submission |
| --- | --- | --- |
| Interim Report 1 | The report on the translations performed. | 1 month |
| Interim Report 2 | Report based on the created promotional materials with pictures. The promotional materials need to be handed over to the contracting authority with the repot and on prepared and printed Professional publication. The printed 4000 copies need to be handed over to the contracting authority | 2 months |
| Final Report | The report based on done digital marketing. With pictures and prof, handed over to the contracting authority with the report. | 6 months |

## Submission & approval of reports

One original and one  copie of the reports referred to above must be submitted to the Contracting Authority. The reports must be written in English.

# MONITORING AND EVALUATION

## Special requirements

Not applicable.